## TestCase
Product Name |  | Daraz | TC Start Date | 2023-09-10 | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Sign Up and Log In | TC End Date | 2023-09-11 | TC Execution End Date | [5 empty] | PASS | 49
Epic |  |  | Test Case Developed By | Shakib Hasan | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by |  | Shahan Ali Pranto | [8 empty] | Out of Scope | 0
[11 empty] | TOTAL | 54
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot Link | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'Daraz' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign Up button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd// 2. Click on Sign Up button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a asterisk | Asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Check asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign Up button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'I'd like to receive exclusive offers and promotions via SMS' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Check checkbox beside 'I'd like to receive exclusive offers and promotions via SMS' |  |  | Passed
8 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign Up button at the right corner 3.Keep mandatory fields blank |  |  | Passed
9 |  |  |  | Checking Full name field is case insensitive | Should accept the provided input | Found as per expectation | AbbCCdd uuXXggDD | 1. Goto the URL https://www.daraz.com.bd/ 2. Input AbbCCdd and uuXXggDD in fullname field |  |  | Passed
10 |  |  |  | Entering blank at first position in Full name field | Should not accept the provided input | Not found as per expectation | Aakk | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Input space at first position of Full name field |  |  | Failed
11 |  |  |  | Entering blank at last position of Full name field | Should not accept the provided input | Not found as per expectation | BBggn | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Input space at last position of Full name field |  |  | Failed
12 |  |  |  | Checking alert message for all mandatory fields if left empty | Should pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
13 |  |  |  | Inputing Full name with special characters | Should not accept the provided input | Found as per expectation | *&&*())**##@%% | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter special characters in Full name field |  |  | Passed
14 |  |  |  | Inputing Full name with numbers | Should not accept the provided input | Not found as per expectation | 66754455 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter numbers in Full name field |  |  | Failed
15 |  |  |  | Inputing Full name with decimal numbers | Should not accept the provided input | Not found as per expectation | 78.7568.99 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter decimal numbers in Full name field |  |  | Failed
16 |  |  |  | Inputing Full name with alphanumeric characters | Should accept the provided input | Found as per expectation | Shahan88 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter alphanumeric characters in Full name field |  |  | Passed
17 |  |  |  | Inputing Full name with alphabets | Should accept the provided input | Found as per expectation | Shahan | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter alphabets in Full name field |  |  | Passed
18 |  |  |  | Entering comma between alphabets for Full name | Should not accept the provided input | Not found as per expectation | sshh,ada | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter commas between alphabets in Full name field |  |  | Failed
19 |  |  |  | Entering space between alphabets for Full name | Should accept the provided input | Found as per expectation | Shahan Ali | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter space between alphabets in Full name field |  |  | Passed
20 |  |  |  | Checking 'I'd like to receive exclusive offers and promotions via SMS' checkbox | Should function successfully | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Select the 'I'd like to receive exclusive offers and promotions via SMS' checkbox |  |  | Passed
21 |  |  |  | Validating a phone number can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | +8801793594239 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Fill the phone number with already registered phone number. |  |  | Passed
22 |  |  |  | Checking password field values are masked | Should be masked | Found as per expectation | check123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter password password |  |  | Passed
23 |  |  |  | Inputing only number in password field. | Should not allow user to register and display a pop message | Found as per expectation | 123123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter only numbers for password. |  |  | Passed
24 |  |  |  | Inputing only alphabet in password field. | Should not allow user to register and display a pop message | Found as per expectation | abcabc | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter only alphabets for password. |  |  | Passed
25 |  |  |  | Inputing weak password length | Should not allow user to register | Found as per expectation | abc1 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
26 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | abc123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
27 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | abc123789 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
28 |  |  |  | Inputing valid data for password | Should allow user to register | Found as per expectation | Abc1516 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
29 |  |  |  | Checking registration with invalid phone number | Should not allow user to register and pop an error message | Found as per expectation | Phone number: 01111111111 Full name: Shahan Ali Pranto Verification code: ***** Password: check123 Gender: Male | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials and an invalid phone number. 4.Click 'Create an Account' |  |  | Passed
30 |  |  |  | Checking confirmation verificatioin code sent to the registered phone number | Sent successfully | Found as per expectation | Phone number: 01793594239 Full name: Shahan Ali Pranto Verification code: ***** Password: check123 Gender: Male | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' 5. Check verification code and confirm account |  |  | Passed
31 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Phone number: 01793594239 Full name: Shahan Ali Pranto Verification code: ***** Password: check123 Gender: Male | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' |  |  | Passed
32 |  |  |  | Inputting wrong verification code. | Should not allow user to register and pop an error message | Found as per expectation | Phone number: 01793594239 Full name: Shahan Ali Pranto Verification code: ***** Password: check123 Gender: Male | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' 5. Check verification code and confirm account |  |  | Passed
33 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Facebook' |  |  | Passed
34 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Google' |  |  | Passed
35 |  |  |  | Checking if already a member, Login redirect link | Allow user to redirect to login page | Found as per expectation | Click on 'Login' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Click on 'Login' at the top right. |  |  | Passed
36 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | shahan123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
37 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
38 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Passed
39 |  | Functionality Testing | Log In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
40 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | shahan123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
41 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | abc@qwe.com shahan123 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
42 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: shahan123@gmail.com Password: Check456 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
43 |  |  |  | Verifying 'Reset Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on Reset Password' 4. Check email |  |  | Passed
44 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on Reset Password' 4. Check the registered email |  |  | Passed
45 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on Reset Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
46 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: shahan123@gmail.com Password: Check456 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
47 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: shahan123@gmail.com Password: Check456 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password |  |  | Passed
48 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: shahan123@gmail.com Password: Check789 | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
49 |  |  |  | Checking Log in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Log in with Facebook' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Login button at the right corner 3. Click on Log in with Facebook |  |  | Passed
50 |  |  |  | Checking Log in with Google' | Should allow user to register | Found as per expectation | Click on 'Log in with Google' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Log in button at the right corner 3. Click on Log in in with Google |  |  | Passed
51 |  |  | Improvement Scopes | Place captcha" for verifying human or robot
52 |  |  |  | A maximum length of the password should be defined
53 |  |  |  | Place check box "remember me" for remembering credentials
54 |  |  |  | Ffirst name and last name should be placed on the registration form
A 'confirm password' field should be added.
Negative test

## Mind Maps
Mindmap for Daraz website testing (Sign up & Log in)

## Report
Test Case Report
Project Name | Daraz
Module Name | Sign Up and Log In |  |  |  |  | Total No. | Status
Test Case Version | [5 empty] | 49 | PASS
Written By | Shahan Ali Pranto |  |  |  |  | 5 | FAIL
Executed By | Shahan Ali Pranto |  |  |  |  | 0 | Not Executed
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 49 | 5 | 0 | 0 | 54
Grand Total | 49 | 5 | 0 | 0 | 54

## Bug Report
Bug Reporting | Bug Reporting
# SL 10 | # SL 18 Issue: Entering comma between alphabets for Full name Reproducing Steps: 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Enter commas between alphabets in Full name field Env: Production Module: Sign Up Severity: P2 Screenshot link of the bug Responsible QA: Shahan Ali Pranto.
Issue: Entering blank at first position in Full name field
Reproducing Steps:
1. Goto the URL https://www.daraz.com.bd/ 2. Click on Sign up button at the right corner 3. Input space at first position of Full name field
Env: Production
Module: Sign Up
Severity: P2
Screenshot link of the bug
Responsible QA: Shahan Ali Pranto.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (54/54)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/54)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (49/54)*100 = 90.74
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/54)*100 = 9.26
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/54)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A